## Sheet1
RESIDENTIAL CONSTRUCTION SCHEDULE
[Project Name]
[Company Name]
TASKS | START DATE | END DATE | DURATION
GENERAL CONDITIONS | 2017-09-22 | 2017-10-30 | 48
Finalize Plans and develop estimate with owner, Architect | 2017-10-22 | 2017-11-15 | 40
Sign Contract and Notice to Proceed | 2018-05-15 | 2018-05-30 | 16
APPLY FOR PERMITS | 2018-05-30 | 2018-06-25 | 27
Secure Foundation Permit | 2018-08-21 | 2018-08-31 | 28
Secure Framing Permit | 2018-09-01 | 2018-09-03 | 29
Secure HVAC Permit | 2018-09-04 | 2018-11-02 | 62
Secure Miscellaneous Permit | 2018-11-03 | 2018-11-28 | 27
SITE WORK | 2018-11-09 | 2018-12-15 | 40
Install Temporary Power Service | 2019-05-15 | 2019-05-30 | 15
Install Underground Utilities | 2019-05-30 | 2019-06-25 | 30
FOUNDATION | 2019-08-21 | 2019-08-31 | 12
Excavate for Foundations | 2019-08-31 | 2019-09-10 | 18
Form Basement balls | 2019-12-12 | 2020-01-04 | 6
Strip Basement Wall Forms | 2020-01-06 | 2020-01-18 | 13
Backfill Formation | 2020-01-10 | 2020-01-15 | 6